## Task
Item | Goal | Task | Estimated Time | Assigned To | Target Deadline | Actual Time | Actual Delivery | Status | Comments
1 | implementation of evolution 1 |  | 0 |  |  | 0
1.1 |  | input parse | 120 minutes | Yuhan Xue | 2024-03-24 | 180 minutes | 2024-03-22 | Completed
1.2 |  | output message sender | 120 minutes | Xueyi Fu | 2024-03-24 | 180 minutes | 2024-03-22 | Completed
1.3 |  | user interface and related class implementation | 75 minutes | All | 2024-03-24 | 150 minutes | 2024-03-22 | Completed | seperate this task to each team member
1.4 |  | lecture and record class implementation | 120 minutes | Yuchen Jiang | 2024-03-24 | 180 minutes | 2024-03-22 | Completed
1.5 |  | setup CI/CD, including automated tests | 120 minutes | Junyan Tang | 2024-03-24 | 180 minutes | 2024-03-22 | Completed
2 | basic modules of evolution 2 |  | 0 |  |  | 0
2.1 |  | client and server socket | 360 minutes | Xueyi Fu | 2024-04-09 | 720 minutes | 2024-04-09 | Completed
2.2 |  | course admin app | 360 minutes | Yuchen Jiang | 2024-04-09 | 720 minutes | 2024-04-09 | Completed
2.3 |  | user admin app | 360 minutes | Yuhan Xue | 2024-04-09 | 720 minutes | 2024-04-09 | Completed
2.4 |  | DAO and interation with DB | 360 minutes | Junyan Tang | 2024-04-09 | 720 minutes | 2024-04-09 | Completed
3 | detail implementation of client and server
3.1 |  | multithread for client | 100min | Xueyi Fu | 2024-04-03 | 100min | 2024-04-03 | Completed
3.2 |  | display function for client | 60min | Xueyi Fu | 2024-04-03 | 60min | 2024-04-03 | Completed
3.3 |  | socket communication between c/s | 60min | Xueyi Fu | 2024-04-03 | 60min | 2024-04-03 | Completed
3.4 |  | user login function | 30min | Xueyi Fu | 2024-04-06 | 30min | 2024-04-06 | Completed
3.5 |  | faculty weekreport function | 80min | Xueyi Fu | 2024-04-07 | 60min | 2024-04-07 | Completed
3.6 |  | student request report | 60min | Xueyi Fu | 2024-04-07 | 60min | 2024-04-07 | Completed
3.7 |  | student notification preference modification | 60min | Xueyi Fu | 2024-04-08 | 60min | 2024-04-08 | Completed
3.8 |  | faculty record attendacne for previous day | 60min | Xueyi Fu | 2024-04-09 | 60min | 2024-04-09 | Completed
3.9 |  | professor choose course | 60min | Xueyi Fu | 2024-04-09 | 60min | 2024-04-09 | Completed
4 | detail implementation of course admin app
4.1 |  | add/remove/update course | 60min | Yuchen Jiang | 2024-04-03 | 60min | 2024-04-03 | Completed
4.2 |  | add/remove/update section | 60min | Yuchen Jiang | 2024-04-03 | 60min | 2024-04-03 | Completed
4.3 |  | add/remove/update attendance | 60min | Yuchen Jiang | 2024-04-04 | 60min | 2024-04-03 | Completed
4.4 |  | course/section/attendance DAO controller | 60min | Yuchen Jiang | 2024-04-05 | 60min | 2024-04-03 | Completed
4.5 |  | Admin User Interface basic frame | 60min | Yuchen Jiang | 2024-04-05 | 60min | 2024-04-05 | Completed
4.6 |  | course/section file input filter | 60min | Yuchen Jiang | 2024-04-06 | 60min | 2024-04-06 | Completed
4.7 |  | Iogin function | 60min | Yuchen Jiang | 2024-04-08 | 60min | 2024-04-07 | Completed
4.8 |  | unit test | 60min | Yuchen Jiang | 2024-04-10 |  | 2024-04-09 | Completed
4.9 |  | double check for remove a course | 60min | Yuchen Jiang | 2024-04-10 | 60min | 2024-04-09 | Completed
5 | detail implementation of user admin app
5.1 |  | refine user interface and professor/student class | 30min | Yuhan Xue | 2024-04-03 | 30min | 2024-04-03 | Completed
5.2 |  | develop inputprocess class to process input | 30min | Yuhan Xue | 2024-04-04 | 30min | 2024-04-03 | Completed
5.3 |  | add/remove/update user in useroperation class | 40min | Yuhan Xue | 2024-04-05 | 40min | 2024-04-04 | Completed
5.4 |  | add/remove user in useradmin class | 60min | Yuhan Xue | 2024-04-06 | 80min | 2024-04-06 | Completed
5.5 |  | update all user information in useradmin class | 40min | Yuhan Xue | 2024-04-06 | 40min | 2024-04-06 | Completed
5.6 |  | finish app.java | 40min | Yuhan Xue | 2024-04-07 | 40min | 2024-04-07 | Completed
5.7 |  | admin register and login | 60min | Yuhan Xue | 2024-04-09 | 90min | 2024-04-09 | Completed
5.8 |  | admin permission to change student name | 120min | Yuhan Xue | 2024-04-10 | 120min | 2024-04-10 | Completed
5.9 |  | unit test | 120min | Yuhan Xue | 2024-04-10 | 300min | 2024-04-11 | Completed
detail implementation of DAO and DB
6.1 |  | initilize database and create database connection | 30min | Junyan Tang | 2024-04-03 | 20min | 2024-04-03 | Completed
6.2 |  | create pojo data type and corresponding interface | 30min | Junyan Tang | 2024-04-04 | 30min | 2024-04-04 | Completed
6.3 |  | implement userdao, attendancedao, coursedao and sectiondao | 120min | Junyan Tang | 2024-04-06 | 120min | 2024-04-06 | Completed
6.4 |  | implement required functions mentioned in issue by others | 120min | Junyan Tang | 2024-04-10 | 120min | 2024-04-10 | Completed
7 | basic modules for evolution 3
7.1 |  | admin app and JavaFX | 10 days | Yuchen Jiang | 2024-04-29 | 9 days | 2024-04-29 | Completed
7.2 |  | React frontend for attendance take app | 10 days | Yuhan Xue | 2024-04-29 | 9 days | 2024-04-29 | Completed
7.3 |  | backend spring boot controller and services | 10 days | Junyan Tang | 2024-04-29 | 9 days | 2024-04-29 | Completed
7.4 |  | handle data transimission logic between backend and frontend | 10 days | Xueyi Fu | 2024-04-29 | 9 days | 2024-04-29 | Completed
8 | detail implementation of admin app and JavaFX
8.1 |  | modify database logic for admin app | 120min | Yuchen Jiang | 2024-04-17 | 120min | 2024-04-17 | Completed
8.2 |  | Javafx client software | 360min | Yuchen Jiang | 2024-04-18 | 450min | 2024-04-18 | Completed
8.3 |  | javafx basic configuration | 60min | Yuchen Jiang | 2024-04-18 | 120min | 2024-04-18 | Completed
8.4 |  | main page implementation | 30min | Yuchen Jiang | 2024-04-19 | 20min | 2024-04-19 | Completed
8.5 |  | router logic implementation | 60min | Yuchen Jiang | 2024-04-19 | 50min | 2024-04-19 | Completed
8.6 |  | table insertion logic | 50min | Yuchen Jiang | 2024-04-20 | 20min | 2024-04-20 | Completed
8.7 |  | merge user admin app and course admin app | 40min | Yuchen Jiang | 2024-04-20 | 20min | 2024-04-20 | Completed
8.8 |  | global file reader implmentation | 40min | Yuchen Jiang | 2024-04-21 | 40min | 2024-04-21 | Completed
9 | detail implementation of react frontend
9.1 |  | initialize the app and change settings | 120min | Yuhan Xue | 2024-04-17 | 120min | 2024-04-21 | Completed
9.2 |  | add login page and home page | 120min | Yuhan Xue | 2024-04-18 | 150min | 2024-04-22 | Completed
9.3 |  | add navbar | 60min | Yuhan Xue | 2024-04-23 | 60min | 2024-04-23 | Completed
9.4 |  | add teach course component for professor | 120min | Yuhan Xue | 2024-04-24 | 240min | 2024-04-26 | Completed
9.5 |  | add attendance components for professor | 180min | Yuhan Xue | 2024-04-25 | 360min | 2024-04-26 | Completed
9.6 |  | separate professor and student components for the same page | 60min | Yuhan Xue | 2024-04-26 | 60min | 2024-04-26 | Completed
9.7 |  | add attendance component sfor student | 120min | Yuhan Xue | 2024-04-27 | 200min | 2024-04-27 | Completed
9.8 |  | add modify attendance component for professor | 120min | Yuhan Xue | 2024-04-27 | 120min | 2024-04-27 | Completed
9.9 |  | add dynamic routing for attendance history of spefic date | 180min | Yuhan Xue | 2024-04-27 | 360min | 2024-04-28 | Completed
10 | design logic for frontend and backend connection
10.1 |  | test signup and storing user data in database | 120min | All | 2024-04-23 | 180min | 2024-04-23 | Completed | group meeting to design together
10.2 |  | design aligned json structure for data transmission between frontend and backend | 180min | All | 2024-04-24 | 240min | 2024-04-24 | Completed
10.3 |  | test login jwt authentication for frontend and backend | 120min | All | 2024-04-25 | 120min | 2024-04-25 | Completed
11 | backend spring boot controller and services
11.1 |  | initialize the basic structure for spring boot | 120min | Junyan Tang | 2024-04-21 | 120min | 2024-04-21 | Completed
11.2 |  | refactor database service | 60min | Junyan Tang | 2024-04-22 | 60min | 2024-04-20 | Completed
11.3 |  | add user related service | 100min | Junyan Tang | 2024-04-23 | 120min | 2024-04-20 | Completed
11.4 |  | add course related service | 100min | Junyan Tang | 2024-04-24 | 120min | 2024-04-20 | Completed
11.5 |  | add attendance related service | 100min | Junyan Tang | 2024-04-25 | 120min | 2024-04-20 | Completed
11.6 |  | implement mail related service | 60min | Junyan Tang | 2024-04-25 | 60min | 2024-04-26 | Completed
11.7 |  | add location service for attendance take | 120min | Junyan Tang | 2024-04-26 | 120min | 2024-04-26 | Completed
11.8 |  | add configurations | 120min | Junyan Tang | 2024-04-26 | 120min | 2024-04-26 | Completed
11.9 |  | add home controller and login controller | 60min | Junyan Tang | 2024-04-27 | 60min | 2024-04-27 | Completed
11.10 |  | add user controllers | 60min | Junyan Tang | 2024-04-27 | 60min | 2024-04-27 | Completed
11.11 |  | add course related controllers | 120min | Junyan Tang | 2024-04-27 | 240min | 2024-04-27 | Completed
12 | backend spring boot dto and repositories
12.1 |  | add user related dto | 120min | Xueyi Fu | 2024-04-18 | 120min | 2024-04-18 | Completed
12.2 |  | add attendance related dto | 120min | Xueyi Fu | 2024-04-21 | 120min | 2024-04-21 | Completed
12.3 |  | add course related dto | 120min | Xueyi Fu | 2024-04-21 | 120min | 2024-04-21 | Completed
12.4 |  | add checkin dto | 60min | Xueyi Fu | 2024-04-22 | 60min | 2024-04-23 | Completed
12.5 |  | add user profile dto | 60min | Xueyi Fu | 2024-04-23 | 60min | 2024-04-23 | Completed
12.6 |  | add user and course repository | 120min | Xueyi Fu | 2024-04-24 | 120min | 2024-04-24 | Completed
12.7 |  | add attendance repository | 60min | Xueyi Fu | 2024-04-25 | 60min | 2024-04-25 | Completed
12.8 |  | add roster and section repository | 120min | Xueyi Fu | 2024-04-26 | 120min | 2024-04-26 | Completed
13 | Test functions for frontend and backend
13.1 |  | test login and jwt | 120min | All | 2024-04-28 | 600min | 2024-04-28 | Completed | group meeting to test together
13.2 |  | test all get requests for frontend and backend | 240min | All | 2024-04-28 | 240min | 2024-04-28 | Completed
13.3 |  | test all post and put requests for frontend and backend | 240min | All | 2024-04-29 | 240min | 2024-04-29 | Completed
13.4 |  | test take attendance for professor | 240min | All | 2024-04-29 | 240min | 2024-04-29 | Completed
13.5 |  | test take attendance for student | 240min | All | 2024-04-29 | 240min | 2024-04-29 | Completed

## Status
Unassigned
Assigned
Started
Testing
Code Review
Completed